## Sheet1
| Week 1-4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Christmas | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Easter | Week 22 | Week 23
| 2019-09-30 | 2019-10-28 | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16 | 2019-12-23 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-20 | 2020-04-13
Phase 1: Reproduce the existing system. Improve the classification filter by exploring various other window types. | [18 empty] | Poster Presentation |  |  | Thesis Deadline
Research and planning the whole project | bar: Week 1-4 to Week 6
Set up Zedboard and recreate the existing system | bar: Week 5 to Week 7
Research on window aggregation for stream data | bar: Week 6 to Week 8
Explore optimal sliding steps for classification filter | bar: Week 7 to Week 9
Analysis performance | bar: Week 8 to Week 10
Phase 2: Adaptive Region-of-Interest
Research on adaptive filter | bar: Week 10
Identify location of object in the frame with extractions method | bar: Week 11 to Week 12
Implement the adaptive filter on the system | bar: Week 12
Analysis performance.
Phase 3: System adopts to the surrounding environment
Explore inter-frame relationships
Experiment with clock gating
Implement object detection algorithm
Analysis performance.
Phase 4: Power usage monitoring
Measure the power usage on Zedboard.
Migrate from Zedboard to ZC702
Analysis the power usage of the system
Debugging
Poster Preparation and Presentation
Thesis Writing

## Sheet2
| Phase 1: Reproducing the existing system and improve the BNN | Research and planning the whole project | Set up Zedboard and recreate the existing system | Research on BNN implementation | Add more catergories to the neural network | Analysis the performance of the system | Phase 2: Improve efficiency of classification filter | Research on window aggregation for stream data | Replace sliding window filter with tumbling window | Analysis the performance of the system | Phase 3: Introduce adaptive filtering and better power monitoring | Research on adaptive filter | Improve classification to adaptive to speed of object | Migrate from Zedboard to ZC702 | Analysis the power usage of the system | Debugging | Poster Preparation and Presentation | Thesis Writing
2019-09-30
2019-10-28
2019-11-04
2019-11-11
2019-11-18
2019-11-25
2019-12-02
2019-12-09
2019-12-16
2019-12-23
2020-01-27
2020-02-03
2020-02-10
2020-02-17
2020-02-24
2020-03-02
2020-03-09
2020-03-16